## Sheet1
Task | Priority | Owner | Status | Start date | End date | Milestone | Deliverable | Notes
Task - 1 | P0 | Kunj Radadiya | Completed | 2026-07-13 | 2026-07-14 | 2D/3D occupancy map of test environment generated via SLAM — map saved and validated for navigation use | — | Studied the Rhino AMR manual and stacker instructions, then generated a 2D navigation map using SLAM. Took 2 days to learn the system, but completed the task efficiently within the given timeline, and continously.
Task - 3 | P2 | Kunj Radadiya | Completed | 2026-07-14 | 2026-07-14 | To study the manuals of Wet Cleaning Robot and Dry cleaning robot first. | — | I have done it.
Task - 4 | P3 | Kunj Radadiya | In progress | 2026-07-16 | 2026-07-16 | To make a Monster Dry Cleaning as well as Wet Cleaning robot performs the tasks of Automatic Charging | — | —
Task - 5 | P1 | Kunj Radadiya | Completed | 2026-07-16 | 2026-07-16 | To Revise the BOM of ESP32 architecture, and MQTT protocols | — | I have completed the BOM as final one for the integration of ESP32 with Rhino AMR
Task - 7 | P1 | Kunj Radadiya | Completed | 2026-07-16 | 2026-07-16 | To create a basic MQTT of connecting a mobile to laptop. | — | —
Task - 6 | P1 | Kunj Radadiya | In progress | 2026-07-17 | 2026-07-17 | To change the better LED's and Buttons in BOM | — | Add the Screws, nuts, washers, and tiny components, and add better LED's
Task - 8 | P1 | Kunj Radadiya | In progress | 2026-07-18 | — | Understand ESP32 architecture in depth — dual-core Xtensa LX6, GPIO, memory map, peripherals (UART/I2C/SPI/ADC), and WiFi/BT radio subsystem | — | Studying official ESP32 technical reference manual and datasheet alongside hands-on GPIO/peripheral testing
Task - 9 | P1 | Kunj Radadiya | Not started | 2026-07-20 | — | Build working knowledge of core networking concepts — IP addressing, MAC addresses, LAN/WAN structure, subnetting, and basic OSI model layers as relevant to ESP32 WiFi/MQTT communication | — | —
Task - 10 | P1 | Kunj Radadiya | Not started | 2026-07-21 | — | Learn REST API fundamentals and practice GET, POST, PUT, and DELETE requests using Postman, to prepare for API-based communication with the floor comm system backend | — | —
Task - 11 | P0 | Kunj Radadiya | Not started | 2026-07-22 | — | Brainstorm and document new implementation ideas for the Floor Communication System — communication architecture, device topology, and data flow between floor nodes | — | —
Task - 12 | P2 | Kunj Radadiya | Not started | 2026-07-23 | — | Prepare CAD designs for Floor Comm System components, if required for enclosure or mounting hardware | — | —
Task - 13 | P3 | Kunj Radadiya | Not started | 2026-07-24 | — | Research injection molding as a manufacturing option for Floor Comm System enclosures/housings — feasibility, cost, and vendor options | — | —
Task - 14 | P2 | Kunj Radadiya | Not started | 2026-07-25 | — | Research and evaluate RFID tag and receiver options for integration into the Floor Comm System | — | —
Task - 15 | P2 | Kunj Radadiya | Not started | 2026-07-27 | — | Research camera options and integration approach for the Floor Comm System | — | —
Task - 16 | P0 | Kunj Radadiya | Not started | 2026-07-28 | — | Implement MQTT-based communication for the Floor Comm System, building on the mobile-to-laptop MQTT setup completed earlier | — | —
Task - 17 | P3 | Kunj Radadiya | Not started | 2026-07-29 | — | Research and select appropriate Molex connectors for the Floor Comm System wiring harness | — | —
Task - 18 | P2 | Kunj Radadiya | Not started | 2026-07-30 | — | Study Industry OS fundamentals as relevant to the Floor Comm System's industrial deployment environment | — | —
Task - 2 | P1 | Kunj Radadiya | Not started | — | — | Make a movement of Rhino AMR from Point A as start position to Point B, then Point B to Point C | — | This isn't started, There is congested area where the AMR tries to drive, so Autonomous can't be done in congested area.